## Calendar of Action Items
Completed | DCA Item | S.M.A.R.T Goals/Action Steps
FALSE | DCA 1 | Allocate sufficient time for Division Implementation Team (DIT) members to support implementation of Effective Innovations (EIs) including Virginia Tiered Systems of Supports (VTSS)
FALSE | DCA 2 | Identify an individual with executive leadership authority, who is able to attend meetings regularly, to include on the DIT.
FALSE | DCA 3 | Designated coordinator(s) are assigned to prepare for and facilitate the DIT meetings, develop meeting agendas, monitor completion of assigned actions and implementation plan, maintain direct and regular contact with executive leader(s), and use knowledge about EIs including VTSS and implementation research in order to make recommendations to the DIT and the executive leader overseeing the DIT
FALSE | DCA 4 | The DLT will have an identified monthly meeting time on the calendar for the upcoming school year.
FALSE | DCA 4 | DIT has assigned meeting roles and responsibilities (e.g., facilitator, recorder, time keeper, norms monitor).
FALSE | DCA 4 | DIT has a process is in place for absent staff to receive updates within 48 hours following the meeting
FALSE | DCA 4 | DIT has a process for assigning designated timelines to action itmes and documenting progess on an action plan
FALSE | DCA 5 | The DLT has an established written process to select EIs which includes an analysis of the following variables: Need for the EI, Fit and alignment with other EIs including VTSS, Resources needed to fully implement, Capacity within the division to successfully use the EI, Evidence to demonstrate effectiveness, & EI’s readiness for usability.
FALSE | DCA 6 | The DLT will have an established written process to align EIs including VTSS that outlines: Conditions that warrant its use, Criteria for selecting people with advanced knowledge of EIs including VTSS to participate in the process, Core components for EIs including VTSS, Documentation of whether or not EI components overlap or inhibit full use of other components including VTSS, Expectations for summarizing alignment results, & A decision-making protocol exists to be used if the alignment results in recommendations to discontinue use of an EI
FALSE | DCA 7 | The division has demonstrated evidence of commitment to support the division’s successful implementation and scale-up VTSS through general fund budget allocations and grant budget allocation.
FALSE | DCA 8 | The DLT will have a draft of the Implementation Plan for VTSS based on the DCA and division data.
FALSE | DCA 8 | The DLT will have an approved Implementation Plan for VTSS based on division data.
FALSE | DCA 9 | The DLT will conduct the first review of use of the Implementation Plan.
FALSE | DCA 9 | The DLT will conduct the second review of use of the Implementation Plan.
FALSE | DCA 9 | The DLT will conduct the third review use of the Implementation Plan.
FALSE | DCA 10 | The DLT will have a written Communication plan which includes: • List of internal and external stakeholder groups (e.g., internal staff represented in the organizational chart, necessary outside agencies, families) • Person(s) responsible for communication with each group • Frequency of communication (e.g., following each monthly team meeting) • Type of information to disseminate and gather from identified stakeholders • Methods of communication (e.g., regularly scheduled meeting, email) • Communication effectiveness survey and timelines for gathering communication survey data
FALSE | DCA 10 | The DLT will make the Communication Plan accessible to all staff.
FALSE | DCA 10 | The DLT will evaluate the effectiveness of the Communication Plan.
FALSE | DCA 11 | The division will have a documented process outlining the steps needed to identify and address barriers.
FALSE | DCA 11 | The DLT will follow-up to determine if barriers were addressed effectively
FALSE | DCA 12 | The division will have a written process to gather policy relevant information to help identify: • Strengths of the state system • Barriers that need to be resolved at the regional and/or state level support division implementation efforts (e.g., state/federal laws, mandated use of funds, interpretation of legislative language)
FALSE | DCA 13 | The DLT will support schools in the use of a fidelity measure for VTSS implementation.
FALSE | DCA 14 | The Data Analyst will begin to make accessible all of the following data: VTSS fidelity data, student outcome data, capacity data, and scale-up data for the school year to the DLT team.
FALSE | DCA 14 | The DIT will have completed the District Capacity Assessment and entered scores into the state database.
FALSE | DCA 15 | The DLT will begin to use all of the following types of data (fidelity data, student outcome data, capacity data, and scale-up) as part of 2022-23 monthly problem solving.
FALSE | DCA 15 | The DLT will begin to use all of the following types of data (fidelity data, student outcome data, capacity data, and scale-up) as part of 2022-23 monthly problem solving.
FALSE | DCA 16 | The DLT will begin to use a problem-solving process as part of monthly DLT meetings.
FALSE | DCA 17 | The DLT will provide the first report to the school board that includes at least five of the following types of information: • Number of schools across the division working to successfully implement VTSS • Each school’s stage of implementation • Development of internal capacity to build structures to support VTSS (leadership, organization, competency) • VTSS fidelity data • Impact on student outcomes • Stakeholder information (e.g., survey data from staff and parents) about implementation supports • Upcoming work to scale-up VTSS and continue improving its use
FALSE | DCA 17 | The DLT will provide the second report to the school board that includes at least five of the following types of information: • Number of schools across the division working to successfully implement VTSS • Each school’s stage of implementation • Development of internal capacity to build structures to support VTSS (leadership, organization, competency) • VTSS fidelity data • Impact on student outcomes • Stakeholder information (e.g., survey data from staff and parents) about implementation supports • Upcoming work to scale-up VTSS and continue improving its use
FALSE | DCA 18 | The DLT will provide guidance to principals and school staff in understanding best practices for BIT composition by focusing on the following: • School-wide assessment/audit of teaming structures to determine if BIT functions are being addressed by an existing team • Cross-departmental team composition (e.g., general education and special education) • Team size • Selection of the personnel to perform key roles on the team (e.g., coordination) • Experience of team members (e.g., successful use of EIs, positive relationships with staff, adequate time to fulfill responsibilities)
FALSE | DCA 18 | The DLT will provide guidance to BIT to coordinate their work with other school initiatives (e.g., discuss alignment of division and school priorities, barriers)
FALSE | DCA 19 | The DLTs will support the development of BIT implementation plans for VTSS.
FALSE | DCA 20 | The DIT (first) support BITs in using data for decision making, ensuring the process for using data includes: • Analysis of all new data that results in a summary of celebrations and precise problem statements • Generation of hypotheses identifying factors contributing the problem • Analysis of data to validate or generate new hypotheses • Refinement of the implementation plan (S.M.A.R.T. goals and activities) to address the problem
FALSE | DCA 20 | The DIT (second) support BITs in using data for decision making, ensuring the process for using data includes: • Analysis of all new data that results in a summary of celebrations and precise problem statements • Generation of hypotheses identifying factors contributing the problem • Analysis of data to validate or generate new hypotheses • Refinement of the implementation plan (S.M.A.R.T. goals and activities) to address the problem
FALSE | DCA 20 | The DIT (third) support BITs in using data for decision making, ensuring the process for using data includes: • Analysis of all new data that results in a summary of celebrations and precise problem statements • Generation of hypotheses identifying factors contributing the problem • Analysis of data to validate or generate new hypotheses • Refinement of the implementation plan (S.M.A.R.T. goals and activities) to address the problem
FALSE | DCA 21 | The Division will use a process for selecting staff (internal and/or external) who will implement EIs including VTSS through the creation of job descriptions that describe pre-requisite knowledge and responsibilities required.
FALSE | DCA 21 | The Division will use a process for selecting staff (internal and/or external) who will implement EIs including VTSS through the use of a selection process that includes the following: • Performance assessment asking individual(s) to demonstrate required knowledge, skills, and abilities (e.g., simulated activity, role-plays, product development) • Feedback provided to individuals to assess their use of feedback (e.g., incorporating feedback into subsequent portions of the selection process)
FALSE | DCA 21 | The division will review the staff selection process to revise the interview protocol if needed to improve the selection process.
FALSE | DCA 22 | The division will have written professional learning plans for all staff (newly selected and existing) assigned to implement or support the implementation of EIs including VTSS that includes: Areas for further development, type of professional learning that will be provided to develop knowledge, skills and abilities, timeline for completing learning, person(s) assigned to support staff.
FALSE | DCA 23 | The DLT will secure training in VTSS by highly competent individuals that are skill based, include opportunities for practice/behavioral rehearsals when applicable, and provide participant feedback
FALSE | DCA 24 | The DLT will plan a system for collecting training effectiveness data throughout the year: • (Pre and post assessment of knowledge and skills • Observation of participants practicing and applying newly acquired skills • Trainer performance feedback (e.g., feedback on training content, training process, delivery)
FALSE | DCA 24 | The DLT will analyze training effectiveness data to inform improvements to content and delivery and inform improvements in recruitment and selection, training, coaching, and other implementation supports
FALSE | DCA 25 | The division will explore the components of the existing coaching system to support schools in their implementation of EIs including VTSS which includes the identified components.
FALSE | DCA 25 | The division will have a documented coaching system to support schools in their implementation of EIs including VTSS which includes the identified components
FALSE | DCA 26 | The division will have a coaching service delivery plan (CSDP) to document coaching supports provided to include: • Stage-based coaching concepts that distinguish supports to BITs and/or school staff • Continuum of coaching strategies needed to develop the team’s knowledge, skills, and abilities (e.g., observation, prompting, modeling, assistance in adapting to local context, fluency building) • Coaching effectiveness measures (VTSS fidelity data, observation, products, coaching satisfaction survey data) • Frequency of coaching • Expectations for the coach’s preparation • Guidelines for providing feedback (e.g., conceptual feedback components, specific behaviors, timelines for providing written feedback)
FALSE | DCA 26 | The DLT will conduct its first review of the CSDP
FALSE | DCA 26 | The DLT will conduct its second review of the CSDP
FALSE | DCA 26 | The DLT will conduct its third review of the CSDP
FALSE | DCA 27 | The DIT will conduct its first assessment of at least 3 sources of coaching effectiveness data (VTSS fidelity data, BIT observations, product reviews, coaching satisfaction survey results (coaching recipients), coaching service delivery adherence data, coaches’ self-reflections using data, coaching logs).
FALSE | DCA 27 | The DIT will conduct its second assessment of at least 3 sources of coaching effectiveness data (VTSS fidelity data, BIT observations, product reviews, coaching satisfaction survey results (coaching recipients), coaching service delivery adherence data, coaches’ self-reflections using data, coaching logs).
FALSE | DCA 27 | The DIT will conduct its third assessment of at least 3 sources of coaching effectiveness data (VTSS fidelity data, BIT observations, product reviews, coaching satisfaction survey results (coaching recipients), coaching service delivery adherence data, coaches’ self-reflections using data, coaching logs).
July
August
September
October
November
December
January
February
March
April
May
June

## DCA Item Scores
Current Score | Item | Action(s)
| 1. There is a Division Implementation Team (DIT) to support implementation of Effective Innovations (EIs) including Virginia Tiered Systems of Supports (VTSS). | Develop a team that isrepresentative of cross-departmental perspectives (e.g., general education and special education) Include team members are selected for: • Experience in using effective innovations including VTSS • Positive working relationships with building leadership and staff Allocate sufficient time to dedicate to DIT functions
| 2. DIT includes an individual with executive leadership authority. | Include at least one executive leader who can make significant decisions within the district to support schools in their use of effective innovations including VTSS without consulting with a higher authority in team composition Have the executive leader consistently attends meetings When scheduling conflicts occasionally occur, the leader makes sure (s)he is provided with relevant information (e.g., decisions and potential barriers that need to be addressed) within 1-2 days after the meeting
| 3. DIT includes a designated coordinator(s). | Include a designated coordinator(s) who performs a lead role on the DIT by: • Preparing for and facilitating the DIT meetings • Developing meeting agendas • Monitoring completion of assigned actions and implementation plan -AND The coordinator(s) • maintain direct and regular contact with executive leader(s) (e.g., before and after RIT and DIT meetings) • use knowledge about EIs including VTSS and implementation research in order to make recommendations to the DIT and the executive leader overseeing the DIT Have adequate time for individual(s) providing coordinationto fulfill responsibilities
| 4. DIT uses an effective team meeting process. | Consistently use the following effective meeting process: • Meets in person at least monthly or more frequently depending on amount of work • Meeting roles and responsibilities are consistently assigned and used (e.g., facilitator, recorder, time keeper, norms monitor) • Process is in place for absent staff to receive updates within 48 hours following the meeting • Assignments and tasks are completed within designated timelines with progress documented on an action plan
| 5. Division has written process for selecting EIs including VTSS. | Establish a written process to select EIs which includes an analysis of the following variables: • Need for the EI • Fit and alignment with other EIs including VTSS • Resources needed to fully implement • Capacity within the division to successfully use the EI • Evidence to demonstrate effectiveness • EI’s readiness for usability Use process consistently
| 6. Division has a written process to align EIs including VTSS. | Establish a written process to align EIs including VTSS that outlines: • Conditions that warrant its use • Criteria for selecting people with advanced knowledge of EIs including VTSS to participate in the process • Core components for EIs including VTSS • Documentation of whether or not EI components overlap or inhibit full use of other components including VTSS • Expectations for summarizing alignment results • A decision-making protocol exists to be used if the alignment results in recommendations to discontinue use of an EI
| 7. Division allocates resources to support implementation of VTSS. | Demonstrate evidence of commitment to support the division’s successful implementation and scale-up VTSS through general fund budget allocations and grant budget allocation
| 8. DIT has an implementation plan for VTSS. | Develop an implementation plan to ensure the division has the capacity to support successful implementation and sustainability of VTSS across schools, using the following data: • Capacity data (e.g., DCA) • Scale-up data (e.g., each school's stage of implementation) • VTSS Fidelity data • Student outcome data Include S.M.A.R.T. goals and specific activities to achieve the goals Receive approval from division executive leadership
| 9. DIT continuously improves use of the implementation plans. | Review use of the implementation pla a minimum of three times per year The review includes documentation of: • Status of activities (e.g., completed, partial, not-started) • Reasons activities are not completed (e.g., insufficient funding, training) • Team decisions (e.g., provide required resources to complete activities, communicating of barriers, next steps) Modifiy plan when data suggest the need
| 10. Division uses a communication plan. | Write communication plan which includes: • List of internal and external stakeholder groups (e.g., internal staff represented in the organizational chart, necessary outside agencies, families) • Person(s) responsible for communication with each group • Frequency of communication (e.g., following each monthly team meeting) • Type of information to disseminate and gather from identified stakeholders • Methods of communication (e.g., regularly scheduled meeting, email) • Communication effectiveness survey and timelines for gathering communication survey data Make it accessible to all staff Use plan consistently Obtain feedback from stakeholders on the effectiveness of communication
| 11. Division uses a process for addressing internal barriers. | Document process outlining the steps needed to identify and address barriers Use process consistently used to remove internal barriers (e.g., policy and guidance documents are revised to support new ways of work, resources are allocated/re-allocated, competing or ineffective initiatives are modified or removed) Follow-up to determines if barrier were addressed effectively
| 12. Division uses a process to report policy relevant information to outside entities. | Develp a written process to gather policy relevant information to help identify: • Strengths of the state system • Barriers that need to be resolved at the regional and/or state level support division implementation efforts (e.g., state/federal laws, mandated use of funds, interpretation of legislative language) Have staff and executive leadership use the process consistently for reporting information to the identified contact liaison with the Regional Agency and/or State Education Agency (SEA)
| 13. DIT supports schools in the use of a fidelity measure for VTSS implementation. | Use a VTSS fidelity measure that is appropriate for assessing VTSS use: • Measure is a research-validated fidelity measure (i.e., highly correlated with or predictive of intended outcomes for VTSS) Support schools' use of fidelity measures as recommended (e.g., proactive orientation of staff to the fidelity measure, administration, scoring, data entry, report generation, and analysis)
| 14. DIT has access to data for VTSS. | Make accessible all of the following data to the DIT : • VTSS Fidelity data • Student outcome data (e.g., universal screening data, progress monitoring data, and summative assessment data) • Capacity data (e.g., DCA) • Scale-up data (e.g., Stages of Implementation Analysis: Where are We Now)
| 15. DIT actively uses different types of data. | Use all of the following types of data for their intended purposes: • Analyze fidelity data to improve implementation supports (e.g., selection, training, coaching supports to ensure VTSS is being implemented as intended) • Use student outcome data (screening, progress monitoring, summative assessments/state test) to determine the impact VTSS is having on student outcomes • Use capacity data for VTSS to enhance leadership, organizational or competency supports • Use scale-up data to create differentiated plans for schools based on their current stage of implementation
| 16. DIT has a process for using data for decision making. | Use a problem-solving process (e.g. Improvement Cycles) at least three times a year Ensure the process includes: • Analysis of all new data that results in a summary of celebrations and precise problem statements • Generation of hypotheses identifying factors contributing or maintaining the problem • Analysis of data to validate or generate new hypotheses • Refinement of the implementation plan including S.M.A.R.T. goals and activities that lead to desired outcomes
| 17. Division provides a status report on VTSS to the school board. | Create a report that includes at least five of the following types of information: • Number of schools across the division working to successfully implement VTSS • Each school’s stage of implementation • Development of internal capacity to build structures to support VTSS (leadership, organization, competency) • VTSS fidelity data • Impact on student outcomes • Stakeholder information (e.g., survey data from staff and parents) about implementation supports • Upcoming work to scale-up VTSS and continue improving its use Disseminated report a minimum of twice per year
| 18. DIT supports the composition of Building Implementation Teams (BITs). | Provide guidance to principals and school staff in understanding best practices for BIT composition by focusing on the following: • School-wide assessment/audit of teaming structures to determine if BIT functions are being addressed by an existing team • Cross-departmental team composition (e.g., general education and special education) • Team size • Selection of the personnel to perform key roles on the team (e.g., coordination) • Experience of team members (e.g., successful use of EIs, positive relationships with staff, adequate time to fulfill responsibilities) Provide guidance to BIT to coordinate their work with other school initiatives (e.g., discuss alignment of division and school priorities, barriers)
| 19. DITs support the development of BIT implementation plans for VTSS. | Ensure BITs support staff to successfully implement VTSS components in the plans Develop the plans using the following data: • Student outcome data • VTSS fidelity data Write plans' goals as S.M.A.R.T. goals Includes specific activities to achieve the goals Link the plans to division priorities within the division improvement plan
| 20. DIT supports BITs in using data for decision making. | Support BITs use of a specific problem-solving process (e.g.Improvement Cycle) at least three times a year Ensure the process for using data includes: • Analysis of all new data that results in a summary of celebrations and precise problem statements • Generation of hypotheses identifying factors contributing the problem • Analysis of data to validate or generate new hypotheses • Refinement of the implementation plan (S.M.A.R.T. goals and activities) to address the problem
| 21. Division uses a process for selecting staff (internal and/or external) who will implement EIs including VTSS. | Create job descriptions that describe pre-requisite knowledge and responsibilities required Use a selection process that includes the following: • Performance assessment asking individual(s) to demonstrate required knowledge, skills, and abilities (e.g., simulated activity, role-plays, product development) • Feedback provided to individuals to assess their use of feedback (e.g., incorporating feedback into subsequent portions of the selection process) Revise the interview protocol as needed to improve the selection process
| 22. Division has a plan to continuously strengthen staff skills. | Have written professional learning plans for all staff (newly selected and existing) assigned to implement or support the implementation of EIs including VTSS that includes: • Areas for further development • Type of professional learning thatwill be provided to develop knowledge, skills and abilities (e.g., attending a professional learning session, independent reading with structured dialogue to reflect on readings) • Timeline for completing learning • Person(s) assigned to support staff -AND- • Time is allocated for staff to develop knowledge, skills, and abilities that are outlined in the plan
| 23. DIT secures training in VTSS for all division/school personnel. | Prioritize training for division staff in VTSS specific data, systems, and practices Have highly competent individuals provide trainings (e.g., trainers have deep knowledge in areas they are providing training and use effective presentation and engagement skills) Provide trainings that are skill based, include opportunities for practice/behavioral rehearsals when applicable, and provide participant feedback
| 24. DIT uses training effectiveness data. | Use the following types of training effectiveness data: • Pre and post assessment of knowledge and skills • Observation of participants practicing and applying newly acquired skills • Trainer performance feedback (e.g., feedback on training content, training process, delivery) Analyze training effectiveness data to: • Inform improvements to content and delivery • Inform improvements in recruitment and selection, training, coaching, and other implementation supports
| 25. Division has a coaching system to support schools in their implementation of EIs including VTSS. | Develop a coaching system to ensure BITs and school staff have equitable access to high-quality coaching to successfully use EIs including VTSS Include the following: • Definition of coaching • Conditions that warrant coaching • Pre-requisite knowledge needed for coaches • Responsibilities of coaches • Selection guidelines for coaches (for existing or new staff that will be assigned divisions to coach) • Allocation of time for staff to provide coaching to BITs and school staff • Statement clarifying coaches’ decision-making authority • Coaching service delivery plan • Communication protocol between coaches and other groups/teams internal and external to the division • Supervision and accountability structures Use the coaching system consistently
| 26. DIT uses a coaching service delivery plan for VTSS. | Document Coaching supports provided to include: • Stage-based coaching concepts that distinguish supports to BITs and/or school staff • Continuum of coaching strategies needed to develop the team’s knowledge, skills, and abilities (e.g., observation, prompting, modeling, assistance in adapting to local context, fluency building) • Coaching effectiveness measures (VTSS fidelity data, observation, products, coaching satisfaction survey data) • Frequency of coaching • Expectations for the coach’s preparation • Guidelines for providing feedback (e.g., conceptual feedback components, specific behaviors, timelines for providing written feedback) Review adherence to the coaching service delivery plans three times a year
| 27. DIT uses coaching effectiveness data. | Assessed coaching effectiveness at least three times a year Use at least three sources of data: • VTSS fidelity data • BIT observations • Product reviews • Coaching satisfaction survey results (coaching recipients) • Coaching service delivery adherence data • Coaches’ self-reflections using data • Coaching logs Utilize coaching effectiveness data to inform improvements in coaching, recruitment and selection, training, and other implementation supports

## Division Priority Goal 1
2022-23 Comprehensive Division Improvement Plan Template
School Division:---
Define (Area of Focus):
Analyze (SMART Goal):
Implement (Essential Action /Research-based Strategy/Evidence-based Intervention):
Action Plan
Action Steps (Place in sequential order) | Position(s) Responsible for Implementation | Implementation Frequency | Evidence/Artifacts: Implementation and Impact | Position(s) Responsible for Monitoring | Monitoring Frequency | Title I, Part A Budget Implications (if applicable)
PRACTICES
SYSTEMS
Supplemental Supports: What additional action steps will be implemented to support achievement, opportunity, and/or access for students?
English Learners |  |  | Students with Disabilities
Economically Disadvantaged |  |  | Transient, Foster and Homeless
Evaluate (Progress Monitoring)
Update | [5 empty] | Date

## Division Priority Goal 2
2022-23 Comprehensive Division Improvement Plan Template
School Division:---
Define (Area of Focus):
Analyze (SMART Goal):
Implement (Essential Action /Research-based Strategy/Evidence-based Intervention):
Action Plan
Action Steps (Place in sequential order) | Position(s) Responsible for Implementation | Implementation Frequency | Evidence/Artifacts: Implementation and Impact | Position(s) Responsible for Monitoring | Monitoring Frequency | Title I, Part A Budget Implications (if applicable)
PRACTICES
SYSTEMS
Supplemental Supports: What additional action steps will be implemented to support achievement, opportunity, and/or access for students?
English Learners |  |  | Students with Disabilities
Economically Disadvantaged |  |  | Transient, Foster and Homeless
Evaluate (Progress Monitoring)
Update | [5 empty] | Date

## Division Priority Goal 3
2022-23 Comprehensive Division Improvement Plan Template
School Division:---
Define (Area of Focus):
Analyze (SMART Goal):
Implement (Essential Action /Research-based Strategy/Evidence-based Intervention): | [5 empty] | ☐ Academic Review Finding
Action Plan
Action Steps (Place in sequential order) | Position(s) Responsible for Implementation | Implementation Frequency | Evidence/ Artifacts: Implementation and Impact | Position(s) Responsible for Monitoring | Monitoring Frequency | Title I, Part A Budget Implications (if applicable)
PRACTICES
SYSTEMS
Supplemental Supports: What additional action steps will be implemented to support achievement, opportunity, and/or access for students?
English Learners |  |  | Students with Disabilities
Economically Disadvantaged |  |  | Transient, Foster and Homeless
Evaluate (Progress Monitoring)
Update | [5 empty] | Date

## School TFI Summaries
School Name | 1.1 - Team Composition | 1.2 - Team Operating Procedures | 1.3 - Behavior Expectations | 1.4 - Teaching Expectations | 1.5 - Problem Behavior Definitions | 1.6 - Discipline Policies | 1.7 - Professional Development | 1.8 - Classroom Procedures | 1.9 - Feedback & Acknowledgement | 1.10 - Faculty Involvement | 1.11 - Student/Family/Community Involvement | 1.12 - Discipline Data | 1.13 - Data-based Decision Making | 1.14 - Fidelity Data | 1.15 - Annual Evaluation | Total TFI Score (out of 30) | Tier I Fidelity % | Tier 1 Fidelity of Implementation - 70% (Yes or No)
Elementary School 1
Elementary School 2
Middle School
High School
etc.
Combined Feature Score (out of 16) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Combined Fidelity % per Feature | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Division Planning Questions
What does tiered data look like for behavior and academics? Is our universal instruction successful?
What are the division priorities over the next 3-5 years? Implementation goals?
Where are the schools compared to our priorities?
Where is the division in implementation?
What can you do to build capacity to support these goals?
School Planning Questions
What are the division's priorities?
What are our priorities as a school?
What does our outcome data tell us?
What patterns do we see in our implementation fidelity?
What are our goals?
Other questions; maybe for small group
Where are we at? Is this a concern? Why?
Is fidelity of implementation important? Why? What are we hoping to change? What outcomes might we affect?
What is our plan for implementation?
What is our capacity?

## FOI 3 years
School | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023
Elementary School 1
Elementary School 2
Middle School
High School
etc.

## Strategic Plan Alignment
The Divisions's Strategic Plan Goals | Related DCA Component (to support building capacity to achieve Division's Strategic Plan Goal) | Related Implementation Matrix Component | Related CAP Essential Action (If applicable)